## Sheet1
Phase | Researcher | Task | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
1. Understanding existing research and re-defining research need | 1 | Reviewing and extending knowledge of existing data augmentation strategies across NLP and non-NLP fields
| 2 | Reviewing and extending knowledge of existing research on constrained text generation
2. Language model architecture selection | 1 | Identify at least three (3) language models that could be candidates for text generation
| 2 | Implement a text classifier to measure the impact of performance of data augmentation
Identify at least one (1) language model that could be a candidate for text generation
3. Prompt finetuning and data preparation | 1, 2 | Explore finetuning strategies and select the most promising results, preprocessing data as required.
4. Model finetuning | 1, 2 | Finetune respective models until satisfied that highest level achievable performance is reached
5. Cross-checking results and experimentation with other dataset | 1 | Share findings and approach with Researcher 2. Explore performance against other datasets.
| 2 | Share findings and approach with Researcher 1. Explore performance against other datasets.
6. Evaluation and write-up | 1, 2 | Agree on a single model (or approach), and present findings in a research paper.